PROJECT CHARTER

ShopEase Customer Churn Reduction Initiative

Version 1.0  |  March 2026  |  Confidential

# 1. Project Overview

ShopEase, a mid-sized e-commerce platform serving 250,000+ active customers, is facing a 27% annual customer churn rate — well above the industry benchmark of 15%. This represents an estimated $4.2M in annual revenue loss and threatens the company's long-term growth trajectory.

This project will deliver a data-driven Customer Churn Prediction and Retention System that identifies at-risk customers early, automates personalized retention outreach, and provides leadership with real-time churn analytics.

# 2. Business Problem & Opportunity

## 2.1 Problem Statement

Current churn management is entirely reactive and manual. Customers are identified as lapsed only after 45–60 days of inactivity, at which point most have already made their next purchase with a competitor. There is no risk scoring, no automated outreach, and no campaign performance tracking.

## 2.2 Business Opportunity

Industry benchmarks indicate that a well-implemented churn prevention system can reduce churn by 30–50%. For ShopEase, reducing churn from 27% to 15% would retain approximately $3.2M in additional annual revenue — a strong business case with estimated project ROI of 420% over 3 years.

# 3. Project Objectives

| # | Objective | Target Metric | Timeline |
| --- | --- | --- | --- |
| O1 | Reduce annual customer churn rate | 27% → 15% | 12 months post-launch |
| O2 | Deploy churn prediction ML model | AUC ≥ 0.80 | Week 8 |
| O3 | Automate retention email campaigns | 40% reduction in manual effort | Week 12 |
| O4 | Increase campaign conversion rate | 4% → 15% | 6 months post-launch |
| O5 | Build executive churn analytics dashboard | Monthly auto-report live | Week 10 |

# 4. Scope

## 4.1 In Scope

- Customer behavioral data pipeline (real-time event streaming)

- ML churn prediction model development and deployment

- CRM (Salesforce) integration for risk score display

- Marketing automation for triggered retention email campaigns

- CSM at-risk customer dashboard with prioritization

- Leadership churn analytics dashboard (Power BI)

- Model monitoring and monthly retraining process

## 4.2 Out of Scope

- Mobile push notification campaigns (Phase 2)

- Churn prediction for B2B enterprise accounts

- Redesign of the customer mobile app or website

- Pricing strategy changes

# 5. Stakeholders

| Name/Role | Organization | Interest/Responsibility | Influence |
| --- | --- | --- | --- |
| VP Customer Experience | ShopEase | Executive sponsor; signs off on go-live | High |
| Head of Data Science | ShopEase | ML model development lead | High |
| Marketing Manager | ShopEase | Owns email campaign activation | High |
| CSM Team Lead | ShopEase | Represents CSM end users | Medium |
| IT/Dev Lead | ShopEase | CRM and pipeline integration | High |
| Data Protection Officer | ShopEase | GDPR/PIPEDA compliance review | Medium |
| Business Analyst (You) | ShopEase | Requirements, process, documentation | Medium |

# 6. RACI Matrix

| Activity | BA | VP CX | Data Science | Marketing | IT/Dev |
| --- | --- | --- | --- | --- | --- |
| Define business requirements | R/A | C | C | C | I |
| Design ML model | C | I | R/A | I | C |
| Build data pipeline | I | I | C | I | R/A |
| CRM integration | C | I | I | I | R/A |
| Campaign design | I | A | I | R | I |
| UAT sign-off | R | A | C | C | C |
| Go-live approval | R | A | C | C | C |

R = Responsible  |  A = Accountable  |  C = Consulted  |  I = Informed

# 7. High-Level Timeline

| Phase | Activities | Duration | Key Milestone |
| --- | --- | --- | --- |
| Phase 1: Discovery | Requirements elicitation, AS-IS process mapping, gap analysis | Weeks 1–2 | BRD Sign-off |
| Phase 2: Design | Solution design, data model, ML architecture, wireframes | Weeks 3–4 | Design approval |
| Phase 3: Build | Data pipeline, ML model training, CRM integration, campaign setup | Weeks 5–8 | UAT entry |
| Phase 4: Test | System testing, UAT, defect resolution | Weeks 9–10 | UAT sign-off |
| Phase 5: Deploy | Phased rollout, training, go-live | Weeks 11–12 | Go-Live |
| Phase 6: Monitor | KPI tracking, model retraining, optimization | Ongoing | 90-day review |

# 8. Budget Summary

| Category | Estimated Cost | Notes |
| --- | --- | --- |
| Data Engineering (Pipeline build) | $45,000 | One-time |
| ML Model Development | $30,000 | One-time |
| CRM Integration (Salesforce) | $15,000 | One-time |
| Marketing Platform (HubSpot) | $12,000/year | Ongoing |
| Cloud Infrastructure (AWS) | $18,000/year | Ongoing |
| Training & Change Management | $5,000 | One-time |
| TOTAL (Year 1) | $125,000 | ROI: ~420% over 3 years |

# 9. Success Criteria & KPIs

- Annual churn rate reduced from 27% to 15% within 12 months of go-live

- ML model achieves AUC ≥ 0.80 on holdout test set before production deployment

- Retention email campaigns achieve ≥ 10% conversion rate within 6 months

- CSM at-risk dashboard used daily by ≥ 90% of CSM team

- Leadership dashboard auto-report delivered monthly with zero manual effort

- Project delivered within approved budget and timeline

# 10. Assumptions & Constraints

## 10.1 Assumptions

- 24+ months of customer purchase history is available in a queryable format

- The Data Science team has experience with Python-based ML model development

- HubSpot can be integrated with the ML scoring system via standard APIs

- CSMs will be available for 3 hours of training prior to go-live

## 10.2 Constraints

- Go-live must occur before Q4 2026 (peak shopping season)

- Total project budget is capped at $130,000 for Year 1

- GDPR/PIPEDA compliance is mandatory and non-negotiable

- No more than 2 hours of CRM downtime permitted during integration

# 11. Charter Sign-Off

| Name | Role | Signature | Date | Decision |
| --- | --- | --- | --- | --- |
|  | VP Customer Experience |  |  | ☐ Approved ☐ Rejected |
|  | Head of Data Science |  |  | ☐ Approved ☐ Rejected |
|  | Marketing Manager |  |  | ☐ Approved ☐ Rejected |
|  | Business Analyst |  |  | ☐ Approved ☐ Rejected |

Document Control: This charter is subject to change control after initial sign-off. Any amendments require re-approval by all signatories.